## FullStack-Template
S.No. | Tasks | Pomodoros | No. of Days | Start Date | End Date | Status | Comments | Doc link
| DOJ |  | 3 Days | 2022-10-10 | 2022-10-10
1 | Course 1 - GIT |  | 3 Days
1.1 | Basic Tutorial | 1 |  | 2022-10-12 | 2022-10-12 | Completed |  | https://www.youtube.com/watch?v=HVsySz-h9r4
1.2 | Git Katas | 15 |  | 2022-10-12 | 2022-10-12 | Completed |  | https://github.com/eficode-academy/git-katas/blob/master/Overview.md#basic-git-katas-in-suggested-order
1.3 | Git Practicsing Scenarios | 9 |  | 2022-10-13 | 2022-10-13 | Completed |  | https://learning.oreilly.com/playlists/6c045404-adc8-4bf0-af29-ac5c614aa7de/
1.4 | How to raise GIT PR? | 1 |  | 2022-10-13 | 2022-10-13 | Completed |  | https://www.loom.com/share/edcaa27a0eca4d0ebabce780fe26584b
1.5 | Git Merge Solution Strategies | 1 |  | 2022-10-13 | 2022-10-13 | Completed |  | https://i.stack.imgur.com/wzol8.gif https://docs.google.com/document/d/1kSZqLVRL5CXaPjE1ISZsZARJg2y-Z1-7TrA5LeWaqsg/edit
1.6 | Git Quiz | 1 |  | 2022-10-13 | 2022-10-13 | Completed |  | https://docs.google.com/forms/d/e/1FAIpQLScvt4_YH2xBKrvzHNyv3MEJG9ACncMlnLwojz7_KAAImReJBg/viewform?authuser=0
1.7 | Git Assignment | 20 |  | 2022-10-14 | 2022-10-17 | Completed |  | https://docs.google.com/document/d/1kGIDEjhBkeFyXnLRZc8-uJZYIjOKthXfb3NtkBGboGc/edit
| Internal Review | [5 empty] | schedule 15 mins session everyday and a 1 hour review after coursework
2 | Course 2 - Problem Solving |  | 6 Days
2.1 | Michigan | 16 |  | 2022-10-18 | 2022-10-18 | Completed |  | https://www.coursera.org/learn/compthinking
2.2 | Penn | 16 |  | 2022-10-19 | 2022-10-19 | Completed |  | https://www.coursera.org/learn/computational-thinking-problem-solving
2.3 | Stanford | 48 |  | 2022-10-20 | 2022-10-24 | In-Progress |  | https://www.coursera.org/specializations/algorithms
2.4 | Assignment | 16 |  | 2022-10-25 | 2022-10-25 | Not Started
| Internal Review | [5 empty] | schedule 15 mins session everyday and a 1 hour review after coursework
3 | Course 3 - HTML |  | 1 Day
3.1 | Getting Started with Web | 2 |  | 2022-10-26 | 2022-10-26 | Not Started |  | https://medium.com/oceanize-geeks/15-html-best-practices-that-developers-should-know-cb02473d293f | FT = 12 | D
3.2 | HTML Course | 12 |  | 2022-10-26 | 2022-10-26 | Not Started |  | https://www.codecademy.com/learn/learn-html https://developer.mozilla.org/en-US/docs/Learn/Getting_started_with_the_web
3.3 | HTML Best Practices | 1 |  | 2022-10-26 | 2022-10-26 | Not Started |  | https://developer.mozilla.org/en-US/docs/Learn/Getting_started_with_the_web
3.4 | 1 pager take aways | 1 |  | 2022-10-26 | 2022-10-26 | Not Started
| Internal Review | [5 empty] | schedule 15 mins session everyday and a 1 hour review after coursework |  | PT = 3 to 6
4 | Course 4 - CSS |  | 1.5 Day
4.1 | CSS Course and Basics | 4 |  | 2022-10-27 | 2022-10-27 | Not Started |  | https://www.codecademy.com/learn/learn-css https://developer.mozilla.org/en-US/docs/Learn/Getting_started_with_the_web/CSS_basics
4.2 | CSS Flexbox | 4 |  | 2022-10-27 | 2022-10-27 | Not Started |  | https://css-tricks.com/snippets/css/a-guide-to-flexbox/
4.3 | Portfolio Assignment | 15 |  | 2022-10-28 | 2022-10-28 | Not Started
4.4 | 1 pager take aways | 1 |  | 2022-10-28 | 2022-10-28 | Not Started
| Internal Review | [5 empty] | schedule 15 mins session everyday and a 1 hour review after coursework
| Course 5 - JavaScript |  | 4.5 Days
5.1 | JavaScript - Best Practices | 1 | Day 1 | 2022-10-31 | 2022-10-31 | Not Started |  | 3. JS-Best Practices https://github.com/airbnb/javascript
5.2 | JavaScript Basics till Objects | 2 | Day 1 | 2022-10-31 | 2022-10-31 | Not Started |  | https://developer.mozilla.org/en-US/docs/Web/JavaScript/A_re-introduction_to_JavaScript
5.3 | Functions and Assignment | 3 | Day 1 | 2022-10-31 | 2022-10-31 | Not Started |  | https://developer.mozilla.org/en-US/docs/Web/JavaScript/Reference/Functions https://docs.google.com/document/d/1APUyGY5XIod0GKFNE3pBXH0sex_K99Ovgod2AAEDw8w/edit
5.4 | Custom Object and Closures | 2 | Day 1 | 2022-10-31 | 2022-10-31 | Not Started |  | https://developer.mozilla.org/en-US/docs/Web/JavaScript/A_re-introduction_to_JavaScript#custom_objects
5.5 | Manipulating DOM | 8 | Day 1 | 2022-10-31 | 2022-10-31 | Not Started | Important Concept | https://developer.mozilla.org/en-US/docs/Learn/JavaScript/Client-side_web_APIs/Manipulating_documents
5.6 | Using Chrome Dev Tools and Quiz | 8 | Day 2 | 2022-11-01 | 2022-11-01 | Not Started |  | https://www.youtube.com/watch?v=x4q86IjJFag https://docs.google.com/forms/d/e/1FAIpQLSdU5SF0zUzwVJ8Rv8aIxdiLASisS1v0WPDLI9H0ee5vgftLfw/viewform?authuser=0
5.7 | Introdcution to node.npm | 2 | Day 2 | 2022-11-01 | 2022-11-01 | Not Started |  | https://nodejs.dev/learn/an-introduction-to-the-npm-package-manager
5.8 | Promises, async -await and Assignment | 6 | Day 2 | 2022-11-01 | 2022-11-01 | Not Started | Important Concept | https://javascript.info/async https://docs.google.com/document/d/1U7UE1LoLeAKmklTgiLPBfDN-W87v-59RPkPXlP7H6bg/edit
5.9 | ES6 Syntax and Assignment | 3 | Day 3 | 2022-11-02 | 2022-11-02 | Not Started | Important Concept | https://codeburst.io/es6-tutorial-for-beginners-5f3c4e7960be https://docs.google.com/document/d/1F_8dnfkb73V159llkwJdjGPjrBvQTKQWOwD3L90zqTM/edit
5.1 | Storage and Assignment | 4 | Day 3 | 2022-11-02 | 2022-11-02 | Not Started | local storage, session storage, Cookies, indexdb | https://developer.mozilla.org/en-US/docs/Web/API/Storage https://developer.mozilla.org/en-US/docs/Web/API/Document/cookie https://docs.google.com/document/d/1olJgmw3WCzmjZagjDsTNnS1CfNdXWVJY6CXIKvNv5uE/edit
5.11 | JS Assignment - Restaurant App | 16 | Day 3 &4 | 2022-11-02 | 2022-11-03 | Not Started |  | https://docs.google.com/document/d/1orNH31crB2SlJDjpQs9kcQnyXIHD8ZNR57Z93lFEzd4/edit?usp=drive_web&authuser=0
5.12 | What and Why Typescript | 3 | Day 4 | 2022-11-04 | 2022-11-04 | Not Started | For code snippets and documentation kindly refer the attached link(videos can be skipped if documentation is good enough) | https://docs.google.com/document/d/1PGVpc9Ewccarr_Egt7-TpoesFcg9vd17dnZCsM2eRvU/edit
Not Started
| FE Assignment 1 - Creating HomePage/Portfolio | 12 | Day 4 | 2022-11-04 | 2022-11-04 | Not Started |  | https://docs.google.com/document/d/1Qzoho9P-vcFa7c0L-cEiZyeQwuDWUXpiEgrveZIldEw/edit
| Internal Review |  |  |  |  | Not Started | schedule 15 mins session everyday and a 1 hour review after coursework
M1 | External Demo/Review - Home Page | [5 empty] | To be endorsed by an external mentor
6 | Course 6 - React |  | 14 Days |  |  | Not Started
6 | Frontend UI - 1.Javascript - Basics (operators, functions, loops, conditionals etc.,) 2.Advanced - Event Loop, Async/Await/Promises, ES6 Syntax, Classes/OOPS 3. HTML -CSS 4.Responsive Web Design 5. Typescript ((interfaces, classes, types etc.,) | 1 | Day 1 | 2022-11-07 | 2022-11-07 | Not Started | Please reflect on the following topics - Quick recap
6.1 | Atomic Structure - Organising Components Assignment | 4 | Day 1 | 2022-11-07 | 2022-11-07 | Not Started |  | https://drive.google.com/file/d/14NmsDvBWys6sP7jtNDNyY7vWiLH1sw0F/view?usp=drive_web&authuser=0 https://docs.google.com/presentation/d/18df9XTg337NeepOXl79lVaafMl_8H0EV9PGKM4VRvV0/edit?usp=drive_web&authuser=0 https://docs.google.com/document/d/1kgu4CaBFpJvbUM-L1F8VEkZFlORb0ChFHbVO62bVqMY/edit
6.2 | Sample React Application with Best Practices | 3 | Day 1 | 2022-11-07 | 2022-11-07 | Not Started |  | https://drive.google.com/file/d/1nuyAhJxxrfizS7cb6V5ASSrmWyojLbe_/view https://github.com/mohammed-atif/reminder-atomic-app-demo https://docs.google.com/document/d/1WAGndAtA7v080cdycACa0MhFNGFLrvrLFA0QUl1QGcc/edit?usp=drive_web&authuser=0
6.3 | Atomic Design - Assignment | 1 | Day 1 | 2022-11-07 | 2022-11-07 | Not Started |  | https://docs.google.com/document/d/16XPNfoA8B34FNIPWtHkcLqfydpAqSw4otmRbdUQRbHY/edit
6.4 | Deploying StoryBook - Chromatic | 1 | Day 1 | 2022-11-07 | 2022-11-07 | Not Started |  | https://www.chromatic.com/builds?appId=62f39e5bf44bd94b776d35be&inviteToken=f06674c16a8c468a96bbe4bfa2bef2d2
6.5 | Virtual DOM | 1 | Day 1 | 2022-11-07 | 2022-11-07 | Not Started |  | https://www.youtube.com/watch?v=RquK3TImY9U https://programmingwithmosh.com/react/react-virtual-dom-explained/ https://reactjs.org/docs/faq-internals.html
6.6 | What and Why TypeScript | 4 | Day 1 | 2022-11-07 | 2022-11-07 | Not Started | For code snippets and documentation kindly refer the attatched link(videos can be skipped if documentation is good enough). We will be following tsx extensions going forward in react | https://www.youtube.com/watch?v=Z5iWr6Srsj8 https://www.youtube.com/watch?v=PL1NUl7fQ2I https://www.typescriptlang.org/docs/handbook/typescript-in-5-minutes.html
6.7 | Storybook Setup | 4 | Day 2 | 2022-11-08 | 2022-11-08 | Not Started | Please find Attached sample storybook | https://storybook.js.org/docs/react/get-started/introduction https://levelup.gitconnected.com/why-you-should-always-use-storybook-when-developing-user-interfaces-4c69b93b2f65 https://sb-blinklist-clone-yaswanth.netlify.app/?path=/story/atoms-inputfield--default&args=placeholder
6.8 | Assignment -Adding Linter and Formater | 1 | Day 2 | 2022-11-08 | 2022-11-08 | Not Started |  | https://docs.google.com/document/d/1uCyXBkCFPrlHV6e-w8s2lqSvj6XLWkAnJf7iPdaFPo0/edit
6.9 | What is a Component and Assignment | 2 | Day 2 | 2022-11-08 | 2022-11-08 | Not Started | Assignment : Code a basic React Component | https://reactjs.org/ https://reactjs.org/docs/static-type-checking.html#using-typescript-with-create-react-app
6.1 | Class vs Functional Components and Assignment | 3 | Day 2 | 2022-11-08 | 2022-11-08 | Not Started |  | https://www.twilio.com/blog/react-choose-functional-components https://docs.google.com/document/d/1KY22MV2CnIIPr1EKMSz1alOLIz0lwROPHEk6VFLJOu8/edit
6.11 | More Intro to React and JSX-Child and Parent Components | 2 | Day 2 | 2022-11-08 | 2022-11-08 | Not Started |  | https://docs.google.com/document/d/1rXoS9r6SBHBhgKwXRUHWQtlWERFuI-6N5jmAzni55vk/edit
6.12 | Assignment -Child and Parent Components | 3 | Day 3 | 2022-11-09 | 2022-11-09 | Not Started |  | https://docs.google.com/document/d/1WbSX0x6SybWpWLOC6zZMtD0ARpMssLWXrRHsgBPbW7I/edit
6.13 | Frontend Framework - Angular, Next.js, Gatsby, Vue.js, Express.js | 2 | Day 3 | 2022-11-09 | 2022-11-09 | Not Started |  | https://buttercms.com/blog/gatsby-vs-nextjs-picking-the-best-react-framework/ https://edg.io/resources/blog/which-modern-frontend-is-the-fastest-react-angular-vue-js/
6.14 | Bundler -Webpack | 2 | Day 3 | 2022-11-09 | 2022-11-09 | Not Started | Go through Part1,Part2 and Part3 of https://www.robinwieruch.de/javascript-project-setup-tutorial. The other links are alternatives | https://www.robinwieruch.de/javascript-project-setup-tutorial https://blog.bitsrc.io/why-learning-webpack-is-important-as-front-end-developer-247bc0ca40bd https://www.freecodecamp.org/news/learn-webpack-for-react-a36d4cac5060/
6.15 | Transpiler - Babel | 3 | Day 3 | 2022-11-09 | 2022-11-09 | Not Started |  | https://www.educative.io/answers/what-is-babel-transpiler
6.16 | Material UI | 2 | Day 3 | 2022-11-09 | 2022-11-09 |  |  | https://material-ui.com/components/buttons/ https://material-ui.com/components/links/
6.17 | ThemeFile | 5 | Day 3 | 2022-11-09 | 2022-11-09 |  | Theming intro-assuming we are using Material UI | https://material-ui.com/customization/theming/ https://docs.google.com/document/d/10_q8_5FzyNU7dQOk6Plw81e4Tumz7fazJt0tpgpVv6A/edit?usp=drive_web&authuser=0 https://mui.com/customization/typography/
6.18 | Story book -Addons | 1 | Day 4 | 2022-11-10 | 2022-11-10 | Not Started | Implement the Storybook Addons | https://storybook.js.org/docs/react/essentials/actions https://storybook.js.org/docs/react/essentials/controls
6.19 | What are Props | 3 | Day 4 | 2022-11-10 | 2022-11-10 | Not Started |  | https://reactjs.org/docs/components-and-props.html
6.2 | useState Management (All Hooks) | 16 | Day 4 and 5 | 2022-11-11 | 2022-11-14 | Not Started |  | https://www.youtube.com/watch?v=QFaFIcGhPoM https://www.youtube.com/watch?v=O6P86uwfdR0
6.21 | React -Basic Inbuilt hooks (useEffect, useState, useContext) and Advanced - inbuilt hooks (useMemo, useCallback etc) and Custom Hooks | 1 | Day 5 | 2022-11-14 | 2022-11-14 | Not Started | Important | https://reactjs.org/docs/hooks-intro.html
6.22 | Event and Form Management | 6 | Day 5 | 2022-11-14 | 2022-11-14 | Not Started |  | https://reactjs.org/docs/handling-events.html
6.23 | Assignment (Blinkist)- State Managment | 10 | Day 5 | 2022-11-14 | 2022-11-14 | Not Started | Now the Folder structure should include theme file with typography, colors and spacing. | https://docs.google.com/document/d/1auiU0905QAPicZtHQkHLMM85lFBkFbGfZYWgREaxHTg/edit
6.24 | Project Scaffolding -Webpack | 5 | Day 6 | 2022-11-15 | 2022-11-15 | Not Started | Build/Set up the folder structure to include webpack config file | https://www.robinwieruch.de/javascript-project-setup-tutorial https://blog.bitsrc.io/why-learning-webpack-is-important-as-front-end-developer-247bc0ca40bd https://www.freecodecamp.org/news/learn-webpack-for-react-a36d4cac5060/
6.25 | Linter and Sonar Cloud Integration | 2 | Day 6 | 2022-11-15 | 2022-11-15 | Not Started | Go through this and reflect on this in the next Standup | https://docs.google.com/document/d/1GqW29h9nkyp1w3f4T51OhDCtshkSGAqmA-_gXw-bUNk/edit
6.26 | Bootcamp(Problem Statement)- Components with Atomic Design and Storybook(with Project Structure) |  | Day 6 and Day 7 | 2022-11-15 | 2022-11-16 | Not Started |  | https://docs.google.com/document/d/1cwexiT0q7cGaWyMLpknJH5A3774jVtPwPmjmTGWG7mg/edit
6.27 | Deploying StoryBook | 1 | Day 8 | 2022-11-17 | 2022-11-17 | Not Started |  | https://reactrouter.com/web/guides/quick-start
6.28 | React Router and SPA | 10 | Day 8 | 2022-11-17 | 2022-11-17 | Not Started |  | https://reactrouter.com/web/guides/quick-start
6.29 | API Handling - (Async, Promises....) | 3 | Day 8 | 2022-11-17 | 2022-11-17 | Not Started |  | https://www.digitalocean.com/community/tutorials/react-axios-react https://reactjs.org/docs/faq-ajax.html https://developer.mozilla.org/en-US/docs/Web/JavaScript/Reference/Global_Objects/Promise
6.3 | Please start working on the Bootcamp(Problem Statement) Simulteniously | 3 | Day 9 | 2022-11-18 | 2022-11-18 | Not Started
6.31 | Mock Server Setup | 1 | Day 9 | 2022-11-21 | 2022-11-21 | Not Started |  | https://github.com/typicode/json-server/blob/master/README.md
6.32 | Assignment - Axios | 5 | Day 9 | 2022-11-21 | 2022-11-21 | Not Started |  | Set up mock server to fetch data from. Make API requests to this mock server and add data to your app.
6.33 | React Testing Library | 12 | Day 9 and Day 10 | 2022-11-21 | 2022-11-22 | Not Started |  | https://testing-library.com/docs/react-testing-library/intro https://www.robinwieruch.de/react-testing-library
6.34 | Redux | 16 | Day 10 and 11 | 2022-11-22 | 2022-11-23 | Not Started |  | https://redux.js.org/introduction/getting-started https://egghead.io/courses/fundamentals-of-redux-course-from-dan-abramov-bd5cc867
6.35 | Other References | 3 | Day 12 | 2022-11-23 | 2022-11-23 | Not Started |  | https://www.robinwieruch.de/categories/react
6.36 | Completion of Bootcamp Problem Statement |  | Day 12 and 13 | 2022-11-23 | 2022-11-24 | Not Started | Create a Multi page App using the concepts learnt so far. Entire flow needs to be done with all screens just like the loom video-Problem Statement | Add PS Figma screens and loom
6.37 | Web Security - 1.OWASP top 10 (XSS, CSRF) 2. 0Auth 2.0 3. Security Headers (CSP, HSTS) | 4 | Day 14 | 2022-11-24 | 2022-11-24 | Not Started |  | https://auth0.com/docs/quickstart/spa/react#add-login-to-your-application
| Internal Review of Bootcamp(PS) App with 1:1 mentor |  | Day 14 | 2022-11-25 | 2022-11-25 | Not Started
M2 | External Demo - Bootcamp Application | [5 empty] | To be endorsed by an external mentor
M3 | Codility - React | [5 empty] | To be conducted by LDP
Backend
| Git Commands Review | [5 empty] | 1:1 Mentor
1 | Course 4 - Java |  | 10 Days |  |  | Not Started
1.1 | Naming Conventions | 3 | Day 1 | 2022-11-28 | 2022-11-28 | Not Started | https://plugins.jetbrains.com/plugin/7973-sonarlint | https://learning.oreilly.com/library/view/clean-code-a/9780136083238/chapter02.xhtml#ch2lev1sec2
1.2 | Naming Conventions - Reflection | 3 | Day 1 | 2022-11-28 | 2022-11-28 | Not Started |  | https://docs.google.com/document/d/1Dfxq2bJ-3kwe5bUhyni_wOYAAiuB5kPwV_SD2BSjI0w/edit
1.3 | Functions - Clean Code |  | Day 2 | 2022-11-29 | 2022-11-29 |  |  | https://learning.oreilly.com/library/view/clean-code-a/9780136083238/chapter03.xhtml
1.4 | SOLID Principles | 5 | Day 3 | 2022-11-30 | 2022-12-01 | Not Started |  | https://docs.google.com/document/d/1mh0HXO5bh2LCTkHLG-tkF8oVznwE4On9Ab8E0GYjITk/edit
1.5 | SOLID Principles - Demo |  | Day 4 | 2022-12-02 | 2022-12-02 | Not Started |  | Develop a single Real Time example that complies to all Solid Principles. Also have the same example with violations of SOLID. Also have the same example with violations of SOLID.After demoing to your 1:1 mentor, Schedule a demo with an external mentor. After demoing to your 1:1 mentor, Schedule a demo with an external mentor
| Solid Principles Demo Feedback Implementation |  | Day 4 |  |  |  |  | Please work on the feedback given by the 1:1 mentor before proceeding to the external demo.
M1 | Solid External Demo |  | Day 5 |  |  |  | To be endorsed by an external mentor
1.6 | Core Java and Assignment |  | Day 6 | 2022-11-29 | 2022-11-29 | Not Started | Install Intellij Community Edition. Use jdk 11. Code alongside the videos. Push you code to git and submit it under Assignment section | https://learning.oreilly.com/videos/the-complete-java/9781801075190/ Kindly Submit your Github links containing the coding examples from the course
1.7 | Java Assignment -1 to 4 |  | Day 7 | 2022-11-30 | 2022-11-30 | Not Started |  | https://docs.google.com/document/d/1bxLW9ZIU9zldQF7ihW0M4ne5XPZJ0HU-UhBaFx-ecA8/edit
1.8 | Java Assignment - 5 to 8 |  | Day 8 | 2022-12-01 | 2022-12-01 | Not Started |  | https://docs.google.com/document/d/1utHf_M0kTIvguLcteXxnC_1jwuPudZ0i9vkDN3vBFN4/edit
1.9 | Java Assignment - 9 to 11 |  | Day 9 | 2022-12-02 | 2022-12-02 | Not Started |  | https://docs.google.com/document/d/1k-XI2kTgLwYNC2WjGuD3IuWzK6s1HGpB4sVf4pxp73I/edit
1.1 | Lamdas and Streams |  | Day 10 | 2022-12-05 | 2022-12-05 | Not Started | Assignment : "Complete the code and push to github. Submit Github link" | https://learning.oreilly.com/videos/java-8-lambdas/9781771374743/
1.11 | Java Assignment - 12 |  | Day 10 | 2022-12-05 | 2022-12-05 | Not Started |  | https://docs.google.com/document/d/1EfzP3XDWuGjv_4A_6H4C19hBYpzRNi1NplxtncLjoBg/edit
| Internal Review |  |  |  |  | Not Started | schedule 15 mins session everyday and a 1 hour review after coursework
M2 | Java Completion and Assignment Review | [5 empty] | Spot Check
M3 | Java Codility | [5 empty] | To be conducted by LDP
2 | Course 5 - DBMS |  | 5 Days
2.1 | DBMS Course |  | Day 1 | 2022-12-06 | 2022-12-06 | Not Started |  | https://learning.oreilly.com/library/view/learning-sql-3rd/9781492057604/
2.2 | DBMS Quiz 1, 2 and 3 |  | Day 1 | 2022-12-06 | 2022-12-06 | Not Started |  | https://docs.google.com/forms/d/e/1FAIpQLSf4JwvrM9-F_Xe_3kBmdZne7LS9cKQxvZOehMk5LK7DVOup7Q/viewform https://docs.google.com/forms/d/e/1FAIpQLScqw_rs6MItDM6Fs4Cl81OHTtiEmu99VR8bxwbFv3tBoz9zsg/viewform https://docs.google.com/forms/d/e/1FAIpQLSfLC73Mp-zwaSjrcxWneOnZF7NQrn5XCqkxIb07tM5OzmUZ8g/viewform?authuser=0
2.3 | Course Introduction |  | Day 2 | 2022-12-06 | 2022-12-06 | Not Started | Please go through the following links and complete the course | https://docs.google.com/document/d/1sWvVt4LYTlJOtThBV8KixbkOvKp887cJdzNuPu8O6AY/edit
2.4 | Introduction to Databases and DBMS |  | Day 2 | 2022-12-06 | 2022-12-06 | Not Started | Please go through the section Introduction to Databases and DBMS. Click on Enroll, and Audit the course | https://www.coursera.org/learn/database-management#syllabus
2.5 | Relational Data Model and Assignment -1 |  | Day 2 | 2022-12-06 | 2022-12-06 | Not Started |  | https://docs.google.com/document/d/1Ey03imUXbclIpo5861VT9yQJXxvV8nJuBVif27_Uc0U/edit
2.6 | Coursera-Basic Query Formulation with SQL and Assignment |  | Day 3 | 2022-12-07 | 2022-12-07 | Not Started | Go through the module "Basic Query Formulation with SQL" and try to get a better understanding of SQL queries and take the quiz at the end of the module. | https://www.coursera.org/learn/database-management#syllabus
2.7 | Coursera -Extended Query Formulation with SQL and Assignment |  | Day 3 | 2022-12-07 | 2022-12-07 | Not Started | Take the quiz present at the end of module "Extended Query Formulation with SQL". | https://docs.google.com/document/d/1nN7B_enROA35k69n9_52xjhtmIdIlicyF7Hfpp7iZ9M/edit
2.8 | ER Diagrams and Assignment |  | Day 4 | 2022-12-08 | 2022-12-08 | Not Started | Kindly go through the sections "Notation for Entity Relationship Diagrams" and "ERD Rules and Problem Solving" and understand what an ER diagram is. Take both the quizzes present at the end of each module. Notion and ERD | https://www.coursera.org/learn/database-management#syllabus
2.9 | Coursera - Data Modelling and Assignment |  | Day 4 | 2022-12-08 | 2022-12-08 | Not Started |  | https://docs.google.com/document/d/1JK4YT66YygixZROJqubMABxTl_kLMKju75mT7HrUGWw/edit
2.1 | Coursera - Schema Conversion and Assignment |  | Day 4 | 2022-12-08 | 2022-12-08 | Not Started |  | https://docs.google.com/document/d/1pnM87T2MWKfC_4rXfE56Ms-VjdT32wkLSUw4DjAPnVQ/edit
2.11 | Coursera - Normalization Concepts and Assignment |  | Day 4 | 2022-12-08 | 2022-12-08 | Not Started |  | https://docs.google.com/document/d/10vtWDoGRH0va83tMapk7srO9f2m1l_IwPnxCdL5UyMA/edit
2.12 | SQL - Excercise Notes, Triggers and Basics |  | Day 5 | 2022-12-09 | 2022-12-09 | Not Started |  | https://docs.google.com/document/d/1x3LuHtveSu1dHY2eRHQsbmJ4fQtmcwn4I5xdCi1_ti0/edit https://www.edureka.co/blog/triggers-in-sql/
2.13 | SQL Query Assignment -1and 2 |  | Day 5 | 2022-12-09 | 2022-12-09 | Not Started |  | https://docs.google.com/document/d/1x3LuHtveSu1dHY2eRHQsbmJ4fQtmcwn4I5xdCi1_ti0/edit
2.14 | Indexes - Query Execution and Optimization |  | Day 5 | 2022-12-09 | 2022-12-09 | Not Started |  | https://learning.oreilly.com/library/view/introduction-to-database/9788131700785/chap7.xhtml#chap7_sub2
2.15 | Assignments: 1. IRCTC 2. Hotel Booking 3. Ecommerce 4. IMBD 5. Paytm |  | Day 5 | 2022-12-09 | 2022-12-09 | Not Started |  | https://docs.google.com/document/d/1dkNneK3eAtx3QRqK8R2Pn2ypll6rYO9QdIfQ8Y-vbbM/edit
| Internal Review |  |  |  |  | Not Started | schedule 15 mins session everyday and a 1 hour review after coursework
3 | Course 6 - Spring&Hibernate |  | 10 Days |  |  |  | Spring Set up | https://drive.google.com/file/d/1B2dDeF8aKz9BPd30GRZ9G5PAnuYr3-L7/view?usp=drive_web&authuser=0
3.1 | Spring Frameworks |  | Day 1 | 2022-12-12 | 2022-12-12 | Not Started |  | https://learning.oreilly.com/videos/spring-framework-essentials/9781491942680/9781491942680-video236091 https://learning.oreilly.com/playlists/61e14101-f1a6-46b6-a05c-3231e58f4436
3.2 | Spring Overview |  | Day 1 | 2022-12-14 | 2022-12-14 | Not Started | Please go through 2,3,4,5 Folders | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
3.3 | Maven-Learning Resources |  | Day 2 | 2022-12-15 | 2022-12-15 | Not Started |  | https://www.youtube.com/watch?v=p0LPfK_oNCM
3.4 | Maven - Course |  | Day 2 | 2022-12-15 | 2022-12-15 | Not Started |  | https://drive.google.com/drive/folders/1gFA4JbAhoa7f0VOTj3Df36WLYaAcLlnu
3.5 | Spring - MVC |  | Day 3 | 2022-12-16 | 2022-12-16 | Not Started | Please go through 11 to 17 Folders - Important | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
3.6 | Spring - DTO's |  | Day 4 | 2022-12-19 | 2022-12-19 |  |  | https://www.baeldung.com/entity-to-and-from-dto-for-a-java-spring-application https://medium.com/learnwithnk/best-practices-in-spring-boot-project-structure-layers-of-microservice-versioning-in-api-cadf62bd3459
3.7 | Spring Beans Scopes and Lifecycle |  | Day 4 | 2022-12-20 | 2022-12-20 | Not Started |  | https://drive.google.com/drive/folders/1GO-On-avt54pkJHfx51trvm7JYfN3iF-
3.8 | Assignment - Logger and Sonar Cloud |  | Day 5 | 2022-12-21 | 2022-12-21 | Not Started |  | https://docs.google.com/document/d/1uCQA3g5LI3OD2t4FSKi9YUcSNzYTiTopv4GnHtWZGPo/edit
3.9 | Use Lombok for boiler plate code |  | Day 6 | 2022-12-22 | 2022-12-22 | Not Started |  | https://projectlombok.org/
3.1 | Spring Configuration |  | Day 6 | 2022-12-22 | 2022-12-22 | Not Started | Please go through 7 to 10 Folders | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
3.11 | Introduction to Hibernate |  | Day 6 | 2022-12-22 | 2022-12-22 | Not Started | Please go through 18 & 19 Folders | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
3.12 | Hibernate CRUD and Configurations |  | Day 7 | 2022-12-23 | 2022-12-23 | Not Started | Please go through 20 & 21 Folders - Important | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
3.13 | Hibernate Advanced Mappings |  | Day 8 | 2022-12-26 | 2022-12-26 | Not Started | Please go through 22 to 27 Folders -Important | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
3.14 | Database WebApp |  | Day 8 | 2022-12-26 | 2022-12-26 | Not Started | Please go through 28 to 33 Folders | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
3.15 | AOP |  | Day 9 &10 | 2022-12-27 | 2022-12-27 | Not Started | Please go through 34 to 45 Folders | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
| Internal Review | [5 empty] | schedule 15 mins session everyday and a 1 hour review after coursework
4 | Course 7 - SpringBoot |  | 8 Days |  |  |  | 8 days for this Module
4.1 | Spring Security (Implementation is Stretch Goal) |  | Day 1 | 2022-12-28 | 2022-12-28 | Not Started | Please go through 47 to 55 Folders | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
4.2 | Spring Rest |  | Day 2 | 2022-12-29 | 2022-12-29 | Not Started | Please go through 56 to 68 Folders | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
4.3 | Spring Boot |  | Day 3 | 2022-12-30 | 2023-01-02 | Not Started | Please go through 70 to 80 Folders | https://drive.google.com/drive/folders/1T4p2ajBIo6ACO09oCbra-fzvbk1rYwpx
4.4 | JUnit&Mockito -Java SpringBoot Unit Testing |  | Day 4 | 2023-01-03 | 2023-01-03 | Not Started |  | https://www.udemy.com/course/mockito-tutorial-with-junit-examples
4.5 | Maven Assignment -1 |  | Day 5 | 2023-01-04 | 2023-01-04 | Not Started |  | After developing Spring application, package it in maven and push the jar file to GIT.
4.6 | JUnit Tests - Naming Conventions |  | Day 5 | 2023-01-04 | 2023-01-04 | Not Started | There is no hard and fast rule, depends on project requirements. Find a convention that suits our needs and stick with it | https://osherove.com/blog/2005/4/3/naming-standards-for-unit-tests.html https://medium.com/@stefanovskyi/unit-test-naming-conventions-dd9208eadbea
4.7 | Spring Boot Assignment |  | Day 6 - 8 | 2023-01-05 | 2023-01-09 | Not Started |  | https://docs.google.com/document/d/1aXixvXFGUN9ybn-_CtTPi1sBcNpTX_zl1FmImE1CwUs/edit
| Internal Review |  |  |  |  | Not Started | schedule 15 mins session everyday and a 1 hour review after coursework
M4 | Spring Boot - External Demo | [5 empty] | To be endorsed by an external mentor
M5 | Spring - Codiltiy | [5 empty] | To be conducted by LDP
Formulas:
End Date = [Start Date]
End Date = workday([Start Date],0)
Start Date = workday([End Date, row above],0)
Start Date = WORKDAY([End Date, row above],1)

## Coursera Loom Videos
Name | Course Name | Loom Video links
Jagadeesh | Michigan- week1 | https://www.loom.com/share/749e998ba4c34a8389dcd25a871b051e
| Michigan- week2 | https://www.loom.com/share/0b08f2407a60438ea1fa1894cb39783b
| Michigan- week3 | https://www.loom.com/share/51c1a6f2c9c5476aa2c1e6c2cb658446
| Michigan- week4 | https://www.loom.com/share/3fd82cabd18649fabb40ec52043a2b02
| Michigan- week5 | https://www.loom.com/share/d848078d54644cb3b7d68e1c93565130
| penn- week1 | https://www.loom.com/share/239f6d8fbd30493292ff20c05e5a72ff
| penn- week2 | https://www.loom.com/share/06c555c9cd4c47b1ae39dea0eb0f5c91
| penn- week3 | https://www.loom.com/share/c8c3437e9bdc4e0badfaf8cdcb0bb4d7
| penn- week4 | https://www.loom.com/share/7aec1feda7a240dda7d6706578c98957
Standford
Chathurvedi | Michigan- week1 | https://www.loom.com/share/dfef184304b64907bb95767983513bc7
| Michigan- week2 | https://www.loom.com/share/8c10506d88724fe48cefb49e62b61f01
| Michigan- week3 | https://www.loom.com/share/5367afa8284849e29e6a3c47cfd3cf63
| Michigan- week4 | https://www.loom.com/share/de7688e815d64f37afea5be43c10b969
| Michigan- week5 | https://www.loom.com/share/99553d232db8403482789a0102bc16ab
| penn- week1 | https://www.loom.com/share/0da4574a363545ebbfc9b0a97dd421a6
| penn- week2 | https://www.loom.com/share/62012a705dc54410b6ea2e76c5d116e8
| penn- week3 | https://www.loom.com/share/9896565b57534eaa9d579dbb7645030a
| penn- week4 | https://www.loom.com/share/5f16fc8c10f7470388bbc90abe5eaca6
Standford
Sai Charan Pabbathi | Michigan- week1 | https://www.loom.com/share/274bdb6beedb421f91991fe0db7dc5ba
| Michigan- week2 | https://www.loom.com/share/1975a134ca244d4d8b64b291236df15a
| Michigan- week3 | https://www.loom.com/share/8d7f0aa0aef944da8067b5f68519c234
| Michigan- week4 | https://www.loom.com/share/3336a84f1fc6489e9466123813abda1d
| Michigan- week5 | https://www.loom.com/share/3ccb712759de4b5ea5ad2e4dc613c74a
| penn- week1 | https://www.loom.com/share/7bed77ee8dab492d9d0083cfa675031e
| penn- week2 | https://www.loom.com/share/6856a5d2b3b44b80abcb5539ce795e11
| penn- week3 | https://www.loom.com/share/1f2450b2391e47b791a8d665b3f68593
| penn- week4 | https://www.loom.com/share/08415cc6a55746e19ac758d50a72729e
Standford
Shaik Shakeel | Michigan-week1 | https://www.loom.com/share/eb733f69c6e24177a36147bcfc6ad751
| Michigan-week2 | https://loom.com/share/b73a0f7d9a184cca84c7ff7357fcdc64
| michigan-week3 | https://loom.com/share/a54a5aac64b540d198251848ad604b89
| michigan-week4 | https://loom.com/share/2867dca76192470fa2c1918e5a8ab15c
Vinay Srikrishna | Michigan week 1 | https://www.loom.com/share/52393c1d0ebd4ae1a7f2e78f8be6278c
| Michigan week 2 | https://www.loom.com/share/f5d3eb4c4d30434181c262307d2e0494
| Michigan week 3 | https://www.loom.com/share/088e47162938493fbb0f7dd46df3a0b0
| Michigan week 4 | https://www.loom.com/share/c325765c57a448df9ba728262a57f38f
| Michigan week 5 | https://www.loom.com/share/cc9badfd0e83432b82c8aebbe0666743
| Penn week 1 | https://www.loom.com/share/edb479a8f2424a2c9293630888e07c44
| Penn week 2 | https://www.loom.com/share/d648e8de525f48a2b4274f8264f45d38
| Penn week 3 | https://www.loom.com/share/d75316877b6640f9a1a000703a73ffbf
| Penn week 4 | https://www.loom.com/share/a8e530096a684099b3638aedd449d27c
Sekhar Dileep | Michigan week 1 | https://www.loom.com/share/3a38d1ec49d84f70be5e7bc8668ca3c6
| Michigan week 2 | https://www.loom.com/share/5043aee95c11456d97d25cffcf5d75c8
| Michigan week 3 | https://www.loom.com/share/01b564a0078f44e8ad57802ce604923a
| Michigan week 4 | https://www.loom.com/share/fc3edfb3329f4ca1bafae60e1209e08a
| Michigan week 5 | https://www.loom.com/share/f2094e6e4ae748f0af0ea60c666b0096
| Penn week 1 | https://www.loom.com/share/8dc55d5baa87486fa28739b4d99f0d2b
| Penn week 2 | https://www.loom.com/share/22042862042e42d09beb977751f4352e
| Penn week 3 | https://www.loom.com/share/200eec83786040869d15aab51784446d
| Penn week 4 | https://www.loom.com/share/616f63e48db74da2ba7b966a54fe43da
Makthal Thana | Michigan week 1 | https://www.loom.com/share/edd19a3098c8400e8717dab06a8843d2
| Michigan week 2 | https://www.loom.com/share/61a72aadaadb4252aefed9f3639c75aa
| Michigan week 3 | https://www.loom.com/share/4717b8bf41b24b1b9f9f1487569dd45c
| Michigan week 4 | https://www.loom.com/share/0c02bac8f35347bfbf458c1e35bf999b
| Michigan week 5 | https://www.loom.com/share/ecd9decf87e3419790e21cf9cf2740b4
| Penn week 1 | https://www.loom.com/share/13af4d7246084f34a36678bcf86afe1b
| Penn week 2 | https://www.loom.com/share/222ebffaf04e44b79b7da47a0236b1ea
| Penn week 3 | https://www.loom.com/share/98eb641660d241b78810bad77755fca9
| Penn week 4 | https://www.loom.com/share/dde19ff99afc406899d326853268a628
| Standford week-1 | https://www.loom.com/share/982383b708f642c088d13f2d63ed701b
| Standford week-2 | https://www.loom.com/share/08637eb3db74451384adb26114bb2310
Venkatalakshmi | Michigan week1 | https://www.loom.com/share/02eee20a4bb349e9bb13f81c9e372133
| Michigan week2 | https://www.loom.com/share/21073a4f8e1341e1a7d52718c2a8b244
| Michigan week3 | https://www.loom.com/share/326410f1a538472090b08144bc403412
| Michigan week4 | https://www.loom.com/share/1ac9352c90254a6993f4c6545d633eab
| Michigan week5 | https://www.loom.com/share/6edfaae713954c14ab1be63ae463237e
| Penn week1 | https://www.loom.com/share/1b7dbac72a5842f4944cc9e76ab6248b
| Penn week2 | https://www.loom.com/share/0fea37369b3c4cdda3fd48b1bd937266
| Penn week3 | https://www.loom.com/share/b5e73cd2dfea48289a2a74feff6feca4
| Penn week4 | https://www.loom.com/share/1b1222941cf44c54a1ae9935de923cb2
Mahitha Kamarapu | Michigan week1 | https://www.loom.com/share/5ba8d3a1001e4d85b93d6e00fb36337e
| Michigan week2 | https://www.loom.com/share/da7f957c66004c8296b609cb05c6b6b8
| Michigan week3 | https://www.loom.com/share/55ec91f049354fc097755255eb318ad5
| Michigan week4 | https://www.loom.com/share/2eca567405d44c669537e38abf6d78ab
| Michigan week5 | https://www.loom.com/share/498623fac4a04291869cec3810776c6a
| Michigan week5 | https://www.loom.com/share/55be14742a0d4c1e9f92e4a47b9744b7
| Penn week1 | https://www.loom.com/share/e18c447d64624367893e391948feb08f
| Penn week2 | https://www.loom.com/share/ff03f09512084a3f95353806a5ce78b0
| Penn week3 | https://www.loom.com/share/fabb6b139c3d47378339c53f86f4a8f9
| Penn week4 | https://www.loom.com/share/8566738d160846059af5942e79bb37e4
| Stanford week1 | https://www.loom.com/share/87aa98c71a7b40b1a9f751a1bec8f626
Stanford week2
Abhishek Goud Bandameedi | Michigan week1 | https://www.loom.com/share/767784f499b244e1bda094004e55c02f
| Michigan week2 | https://www.loom.com/share/6fa46b870afd413a934e2dbd19161859
| Michigan week3 | https://www.loom.com/share/f192701ee2fc4ac8918a0f59169ef1cb
| Michigan week4 | https://www.loom.com/share/f6d0bdb504a34db78e5bf7902494c2e9
| Michigan week5 | https://www.loom.com/share/8c9459a887db4d86ac727ca3a13d5aa4
| Penn week1 | https://www.loom.com/share/f8afd91a34e24217b8d5847d18527106
| Penn week2 | https://www.loom.com/share/089fa434906e4cce8a7761be534fcf29
| Penn week3 | https://www.loom.com/share/b65167f468404571a3cce213549d59ce
| Penn week4 | https://www.loom.com/share/c2438742204d4dc9b480fa67542a1449
Stanford
Atmakur Ramakanth Reddy | Michigan Week 1 | https://www.loom.com/share/b15eb68e255141d8a794d3beb8d6cdcd
| Michigan Week 2 | https://www.loom.com/share/d3d028b4a7044a07b86290b044cf47ae
| Michigan Week 3 | https://www.loom.com/share/ebe0504bc40e4448b84045d88890b7f3
| Michigan Week 4 | https://www.loom.com/share/acb098863dcb48659236934a6e13c984
| Michigan Week 5 | https://www.loom.com/share/fff618da01834b3ca190fdae52eaf9ed
| Penn week 1 | https://www.loom.com/share/000c948025b54d88b3526756fa19bfc8
| Penn week 2 | https://www.loom.com/share/e619b3dd0716465e8bc0a8542cbbe209
| Penn week 3 | https://www.loom.com/share/5fdeacb3f82940a986e68f1687a53249
| Penn week 4 | https://www.loom.com/share/d40aed5210494a2ab3aeed01ade60bff
Stanford Course
SHIVANI CHINTA | Michigan- week1
Michigan- week2
Michigan- week3
Michigan- week4
Michigan- week5
penn- week1
penn- week2
penn- week3
penn- week4
Standford-D&C-week1
Standford-D&C-week2
Standford-D&C-week3
Standford-D&C-week4
Standford-Graph-week1
Standford-Graph-week2
Standford-Graph-week3
Standford-Graph-week4
Standford-Greedy-week1
Standford-Greedy-week2
Standford-Greedy-week3
Standford-Greedy-week4
Standford-NP-week1
Standford-NP-week2
Standford-NP-week3
Standford-NP-week4
Standford-NP-week5
Kota Lakshmi Priya | Michigan- week1
Michigan- week2
Michigan- week3
Michigan- week4
Michigan- week5
penn- week1
penn- week2
penn- week3
penn- week4
Standford-D&C-week1
Standford-D&C-week2
Standford-D&C-week3
Standford-D&C-week4
Standford-Graph-week1
Standford-Graph-week2
Standford-Graph-week3
Standford-Graph-week4
Standford-Greedy-week1
Standford-Greedy-week2
Standford-Greedy-week3
Standford-Greedy-week4
Standford-NP-week1
Standford-NP-week2
Standford-NP-week3
Standford-NP-week4
Standford-NP-week5
Sri Charan | Michigan week 1 | https://www.loom.com/share/ebdad5cc5e334af9a8797366f5b6c394
| Michigan week 2 | https://www.loom.com/share/fece260114ae4c05aa0f0088ed8d8f9b
| Michigan week 3 | https://www.loom.com/share/44087fbf63374f7ab058699674b7b3f4
| Michigan week 4 | https://www.loom.com/share/8e7bf13e9a71449bb230218a0c382519
| Michigan week 5 | https://www.loom.com/share/8ca81084b78c4b74a38e715c4695d1ce
Penn Week 1
Penn Week 2
Penn Week 3
Penn Week 4
| Stanford-D&C Week 1 | https://www.loom.com/share/ee4bba30cf4246439d0f0cfb7717beab
Stanford-D&C Week 2
Stanford-D&C Week 3
Stanford-D&C Week 4
Standford-Graph-week1
Standford-Graph-week2
Standford-Graph-week3
Standford-Graph-week4
Standford-Greedy-week1
Standford-Greedy-week2
Standford-Greedy-week3
Standford-Greedy-week4
Standford-NP-week1
Standford-NP-week2
Standford-NP-week3
Standford-NP-week4
Standford-NP-week5

## October
Name | Module | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30 | 2022-10-31
Yella Sri Charan |  | 2022-10-11: git basic tutorial video; 2022-10-12: hands on practice on git commands; 2022-10-13: practice git basic commits, merging & its conflicts, PRs & git kata; 2022-10-14: Practised katacode scenarios; 2022-10-17: practiced & cleared doubts about git rebase and submitted the assignment; 2022-10-18: Completed Michigan Course; 2022-10-19: Completed Penn Course; 2022-10-20: Started Stanford D&C Course
Kota Lakshmi Priya |  | 2022-10-11: git basic tutorial video; 2022-10-12: hands on practice on git commands; 2022-10-13: practice git commands, Merging, merge conflicts, Raise PR, git kata; 2022-10-14: Completed katas; 2022-10-17: michigan week 1; 2022-10-18: completed michigan; 2022-10-19: penn-1 week; 2022-10-20: completed penn
Shivani Chinta |  | 2022-10-11: git basic tutorial video; 2022-10-12: hands on practice on git commands; 2022-10-13: Git katas commands merging, push , pull; 2022-10-14: completed git katas, merge conflicts,revert,rebase; 2022-10-17: Did michigan course of 2 weeks; 2022-10-18: Completed michigan Course; 2022-10-19: Completed Penn Course; 2022-10-20: Started Stanford D&C Course
VUPPALA VENKATA SAI VISHWANATH RAHUL |  | 2022-10-11: Watched basic git tutorial and additonal video; 2022-10-12: Created zemoso git account, repository and implemented commands; 2022-10-13: Git katas commands like commit,push,pull; 2022-10-14: completed katad; 2022-10-17: Did michigan course of 2 weeks; 2022-10-18: Completed michigan; 2022-10-19: Did 2 weeks of penn course; 2022-10-20: Done with penn course and started stanford D&C course almost done with first week
Maduthuri Soma Sri Sekhar Dileep |  | 2022-10-11: git basic tutorial video; 2022-10-12: hands on practice on git commands; 2022-10-13: Hands on practice on Katas commands,branches in git.; 2022-10-14: merge conflicts,revert,rebase; 2022-10-17: Practiced Git katas; 2022-10-18: completed michigan course; 2022-10-19: Done with the penn course
Vinay Srikrishna Kurada |  | 2022-10-11: git basic tutorial video; 2022-10-12: hands on practice on git commands; 2022-10-13: Katas commands,create diff branches in git; 2022-10-14: Done with the git assignment and quiz; 2022-10-17: Done with the michigan course week 1; 2022-10-18: Done with michigan course; 2022-10-19: Done with the penn course; 2022-10-20: Done with Stanford course week 1 and week 2
Venkatalakshmi Maddu |  | 2022-10-11: git basic tutorial video; 2022-10-12: created github account and repository and practiced commands.; 2022-10-13: git, github, practiced git commands(push, commit, pull....); 2022-10-14: done assignment,quiz and kata commands; 2022-10-17: michigan week 1, 2 course completed; 2022-10-18: Michigan course completed; 2022-10-19: Penn course completed; 2022-10-20: In stanford course 1 week 1,2 are completed
Chathurvedi Jarugu |  | 2022-10-13: revied,practiced git commands & architecture; 2022-10-14: completed quiz,assignment and kata commands; 2022-10-17: completed michigan week 1 course; 2022-10-18: completed michigan course; 2022-10-19: completed penn course; 2022-10-20: completed week1,2,3 in Stanford,dive and conquer
Naga Jagadeesh Krishna Kandula |  | 2022-10-13: done assignment. practiced git commands; 2022-10-14: advanced commands are done; 2022-10-17: completed michigan week 1,2 course; 2022-10-18: completed michigan course 3,4,5 weeks
Makthal Thana |  | 2022-10-11: Git basic Tutorial Video; 2022-10-12: Git katas and hands on practice; 2022-10-13: Merging,Merging conflits,Solutions,Raise PR; 2022-10-14: worked on some basics and completed assignment; 2022-10-17: completed michigan week 1; 2022-10-18: week-2,3,4,5; 2022-10-19: Completed penn course; 2022-10-20: Completed week-1,2 of standford
Mahitha Kamarapu |  | 2022-10-11: Git basic Tutorial; 2022-10-12: Practice on git commands; 2022-10-13: Stashing,Pull Requests,Raise PR,Merging Conflicts; 2022-10-14: Squashing,Git katas,Completed Quiz and Assignment; 2022-10-17: completed michigan week 1 course; 2022-10-18: Done with the remaining weeks in michigan; 2022-10-19: started penn course; 2022-10-20: completed penn course and started stanford course
shaik shakeel |  | 2022-10-11: Git basic Tutorial vedio; 2022-10-12: hands on practice of git commands, other vedios related to git; 2022-10-13: practice git commands, Merging, merge conflicts, Raise PR, git kata; 2022-10-14: stashing, squashing, quiz , assignment, also completed all the katas; 2022-10-17: completed michigan week 1; 2022-10-18: completed michigan course all weeks; 2022-10-19: started the penn course and completed all the weeks; 2022-10-20: startted standford course
RAMAKANTH REDDY ATMAKUR |  | 2022-10-11: git basic tutorial vedio; 2022-10-12: git commands hands on practice; 2022-10-13: practice git basic katas ,merge conflict,stashing,squashing, hands on practice; 2022-10-14: quiz completed,assignment completed; 2022-10-17: started problem solving; 2022-10-18: michigan all weeks completed; 2022-10-19: started the penn course; 2022-10-20: penn course completed started Stanford Course; 2022-10-21: Stanford course in progress week-1 completed
ABHISHEK GOUD BANDAMEEDI |  | 2022-10-11: git basic tutorial vedio; 2022-10-12: practiced basic git commands; 2022-10-13: practised git basic commands, branches, merging,stashing,squashing; 2022-10-14: completed quiz and assignment; 2022-10-17: started problem solving; 2022-10-18: completed the Michigan course; 2022-10-19: started the penn course; 2022-10-20: completed penn course and started stanford course
Saicharan Pabbathi |  | 2022-10-11: basic tutorial; 2022-10-12: hands on coding practice on git commands; 2022-10-13: revised git command and worked on stashes; 2022-10-14: practiced squashing,stashing,rebase,revert,cleaning,amend; 2022-10-17: started michigan course and understood fork in git; 2022-10-18: completed michigan course; 2022-10-19: completed penn course; 2022-10-20: started stanford course